MissingParkHistory.org

Shop Page Implementation Plan

Platform: Fourthwall  |  Print-on-Demand Merchandise

Version 1.0  |  April 9, 2026

# Executive Summary

This plan covers the end-to-end setup of a merchandise shop on MissingParkHistory.org using Fourthwall as the print-on-demand and e-commerce platform. The shop will sell branded hats, t-shirts, hoodies, stickers, and other items to raise funds and awareness for the Missing Park History project.

Fourthwall was selected because it has zero monthly fees, handles all sales tax as Merchant of Record, provides built-in donation support, and requires no code changes to the existing static HTML site. The shop will live at shop.missingparkhistory.org with a link added to the main site navigation.

# Why Fourthwall (Over Alternatives)

| Feature | Fourthwall | Shopify + Printful | Redbubble |
| --- | --- | --- | --- |
| Monthly Cost | $0 | $39/mo | $0 |
| Sales Tax Handling | Fully handled (MoR) | Shopify handles | Handled |
| Custom Domain | Yes (free) | Yes | No |
| Brand Control | Full | Full | Minimal |
| Donation Support | Built-in | Plugin needed | No |
| Customer Support | Fourthwall handles | You handle | Redbubble handles |
| Code Changes Needed | Nav link only | Nav link only | Nav link only |
| Profit Model | You set price, keep profit above base cost | You set price, pay Printful base + Shopify fees | 10% royalty (fixed) |

# Pricing & Profit Estimates

Fourthwall charges a flat base cost per item (publicly listed in their catalog). You set whatever retail price you want and keep 100% of the difference. The only additional fee is standard credit card processing (2.9% + $0.30 per transaction).

| Product | Base Cost | Suggested Retail | Profit/Unit | Margin |
| --- | --- | --- | --- | --- |
| T-Shirt | ~$10 | $28 | ~$17 | ~61% |
| Hoodie | ~$22 | $48 | ~$25 | ~52% |
| Hat / Baseball Cap | ~$12 | $30 | ~$17 | ~57% |
| Sticker Pack | ~$3 | $8 | ~$4.50 | ~56% |
| Tote Bag | ~$8 | $22 | ~$13 | ~59% |
| Mug | ~$7 | $20 | ~$12 | ~60% |
| Poster / Print | ~$6 | $18 | ~$11 | ~61% |

Note: Base costs are approximate and vary by size/color. Verify exact pricing in the Fourthwall product catalog before setting retail prices. Credit card processing fees (2.9% + $0.30) not deducted from profit estimates above.

# Implementation Plan

Five phases, estimated 2–3 weekends of part-time work total. Phases 1–2 can be done in a single sitting.

## Phase 1: Fourthwall Account & Store Setup (Day 1, ~1 hour)

- Create a Fourthwall account at fourthwall.com (free, no credit card required)

- Choose your store name/slug (e.g., missingparkhistory)

- Customize your storefront: upload the MPH logo, set brand colors (#1B4332 dark green, white), write a brief About section tying the shop to the mission

- Connect your custom subdomain: shop.missingparkhistory.org (add a CNAME record in your DNS provider pointing to Fourthwall)

- Enable the donation feature in Fourthwall settings so supporters can donate at checkout

- Set up your Stripe account for payouts (Fourthwall pays monthly via Stripe)

## Phase 2: Design Your Merch (Day 1–2, ~3–4 hours)

### Design Tools (All Free)

- Canva (canva.com) — best for quick mockups, has t-shirt/hat templates

- Kittl (kittl.com) — better for typography-heavy designs, Fourthwall-recommended

- Fourthwall’s built-in editor — for simple logo placement and text overlays

### Recommended Initial Product Line

Start with 5–7 products to keep it focused. Recommended launch lineup:

- Classic Logo Tee: MPH logo + tagline on front, map graphic or URL on back

- "443" Tee: Bold number with "park history entries censored" subtext — a conversation starter

- Trucker Hat: Embroidered MPH logo or "Protect Park History" text

- Hoodie: Logo front, map or park silhouette on back — premium item, higher margin

- Sticker Pack: Low-cost entry point — logo, "Save Our Signs", park-themed designs

- Tote Bag: Canvas tote with the map graphic — practical, high visibility

- Poster / Art Print: The interactive map as a static art print — unique to this project

### Design Tips

- Export designs as PNG with transparent background, minimum 300 DPI (4500x5400px for t-shirts)

- Use your existing brand colors: dark green (#1B4332), mid-green (#2D6A4F), white

- Keep designs bold and simple — they need to read well at small sizes (hats, stickers)

## Phase 3: Upload Products & Set Pricing (Day 2, ~1–2 hours)

- Browse the Fourthwall product catalog and select the specific product variants (shirt style, hat style, etc.)

- Upload your designs to each product using Fourthwall’s editor — preview the auto-generated mockups

- Set retail pricing for each item (see Pricing & Profit table above for guidance)

- Write product descriptions that connect each item to the mission (e.g., "Every purchase supports the fight to protect our parks’ history")

- Order 1–2 samples of your hero products (t-shirt and hat) to verify quality before going live. Fourthwall offers sample pricing.

## Phase 4: Connect to MissingParkHistory.org (Day 2–3, ~30 min)

This is the only phase that touches your existing codebase.

- DNS Setup: Add a CNAME record for shop.missingparkhistory.org pointing to Fourthwall’s servers (Fourthwall provides the exact value in their custom domain settings)

- Nav Bar Update: Add a "🛒 Shop" link to your site’s navigation bar pointing to https://shop.missingparkhistory.org. This is a single line of HTML added to your nav component.

- Optional — Inline Promo Banner: Add a small banner or callout on the main page (e.g., near the Take Action section) linking to the shop. Example: "Support the project — shop merch that funds the fight."

- Git Commit: Commit the nav bar change and any promo banner additions to the repo with a descriptive message.

## Phase 5: Launch & Promote (Day 3+)

- Do a full end-to-end test: visit the shop, add items to cart, go through checkout (use a test purchase or Fourthwall’s preview mode)

- Verify the custom domain resolves correctly and the SSL certificate is active

- Announce via your Beehiiv newsletter (soft launch to your existing audience first)

- Share on social media with photos of your sample products

- Consider a limited-edition launch item (e.g., "Founding Supporter" tee available only for the first 2 weeks) to create urgency

- Monitor the Fourthwall dashboard for orders, fulfillment status, and customer feedback

# Timeline Summary

| Phase | Time Estimate | Target |
| --- | --- | --- |
| 1. Account & Store Setup | ~1 hour | Weekend 1 |
| 2. Design Merch | ~3–4 hours | Weekend 1 |
| 3. Upload & Price | ~1–2 hours | Weekend 1–2 |
| 4. Connect to Site | ~30 minutes | Weekend 2 |
| 5. Launch & Promote | ~1–2 hours + ongoing | Weekend 2–3 |

Total estimated effort: 7–10 hours spread across 2–3 weekends.

# Key Links & Resources

- Fourthwall Sign Up: fourthwall.com

- Fourthwall Product Catalog: fourthwall.com/products (verify base costs here)

- Fourthwall Launch Guides: fourthwall.com/launch-guides

- Fourthwall Non-Profit Guide: fourthwall.com/non-profits

- Design Tool — Canva: canva.com (free tier is sufficient)

- Design Tool — Kittl: kittl.com (Fourthwall-recommended)

- Fourthwall Custom Domain Setup: fourthwall.com/faq (search "custom domain")

# Risks & Considerations

- Sample quality: Always order samples before going live. Print quality can vary by product and color.

- Shipping times: Fourthwall estimates 5–10 business days. Set expectations clearly on the storefront.

- Tax implications: Fourthwall handles sales tax collection/remittance, but profits are taxable income to you personally. Consult a tax advisor, especially if MPH becomes a nonprofit entity.

- Intellectual property: Ensure all designs use original artwork or properly licensed assets. Do not use NPS logos/arrowhead without permission.

- Platform dependency: Your store lives on Fourthwall’s infrastructure. If they change terms, you’d need to migrate. Low risk given their established track record (200K+ sellers).

# Immediate Next Steps

- Sign up for Fourthwall at fourthwall.com

- Draft 3–5 design concepts in Canva (start with the logo tee and the "443" tee)

- Decide on your subdomain strategy (shop.missingparkhistory.org recommended)

- Ask Claude to help with design mockups, product descriptions, or the nav bar code change when ready

MissingParkHistory.org Shop Implementation Plan v1.0  |  April 9, 2026