Missing Park History

IT Project Plan & Sprint Roadmap

# Project Overview

| Project | MissingParkHistory.org — Feature Improvements & Data Quality |
| --- | --- |
| Repository | github.com/BULLMOOSE1872/missingparkhistory |
| Owner | Mike Beebe (BULLMOOSE1872) |
| Tech Stack | HTML/CSS/JS (single-file), Leaflet.js, GitHub Pages |
| Current State | 874 park entries, embed on Outside Online, SOS before/after/restored photos, FWS Sierra Club exhibit documentation |
| Date | March 20, 2026 |

# Sprint Roadmap Summary

| Sprint | Status | Duration | Priority |
| --- | --- | --- | --- |
| Sprint 1: Data Quality — Narrative Audit | Up Next | 1–2 sessions | Critical |
| Sprint 2: Data Quality — Wayback Link Verification | Planned | 1 session | High |
| Sprint 3: Deep Linking / Shareable Park URLs | Planned | 1 session | High |
| Sprint 4: SEO & Social Sharing Meta Tags | Planned | 1 session | High |
| Sprint 5: Mobile Optimization | Planned | 1–2 sessions | Medium |
| Sprint 6: Photo Lightbox | Backlog | 1 session | Medium |
| Sprint 7: Performance — Split parkData | Backlog | 1–2 sessions | Medium |

# Sprint 1: Data Quality — Narrative Audit

| Status: | Up Next |
| --- | --- |
| Duration: | 1–2 sessions |

## Goal

Scan all 874 park entries for mismatched narratives (wrong park names, copy-paste errors like Rock Creek/Rocky Mountain). Fix all incorrect text and verify geographic accuracy.

## Tasks

| # | Task | Priority | Est. | Done |
| --- | --- | --- | --- | --- |
| 1 | Write script to compare park code/name against narrative text | Critical | 30 min | ☐ |
| 2 | Flag entries where narrative mentions a different park name | Critical | 15 min | ☐ |
| 3 | Flag entries where context-box references wrong park stats | Critical | 15 min | ☐ |
| 4 | Manually review and correct each flagged entry | Critical | 1–2 hrs | ☐ |
| 5 | Cross-check GPS coordinates against park code locations | High | 30 min | ☐ |
| 6 | Commit and push all corrections | High | 10 min | ☐ |
| 7 | Verify corrections on live site | High | 15 min | ☐ |

## Deliverable

Zero narrative/park mismatches across all 874 entries

## Risk / Notes

Some narratives may be intentionally generic — need to distinguish boilerplate from errors

# Sprint 2: Data Quality — Wayback Link Verification

| Status: | Planned |
| --- | --- |
| Duration: | 1 session |

## Goal

Verify all Wayback Machine archive links resolve correctly. Fix or remove broken links.

## Tasks

| # | Task | Priority | Est. | Done |
| --- | --- | --- | --- | --- |
| 1 | Extract all wayback URLs from parkData | High | 15 min | ☐ |
| 2 | Batch-check URL response status codes | High | 30 min | ☐ |
| 3 | Report broken/redirected links | High | 15 min | ☐ |
| 4 | Update or remove broken wayback references | Medium | 30 min | ☐ |
| 5 | Commit and verify on live site | Medium | 10 min | ☐ |

## Deliverable

All wayback links verified working or flagged for manual review

## Risk / Notes

Wayback Machine rate limits may slow bulk checking

# Sprint 3: Deep Linking / Shareable Park URLs

| Status: | Planned |
| --- | --- |
| Duration: | 1 session |

## Goal

Enable direct links to individual park entries (e.g., missingparkhistory.org/?park=INDE) so users and journalists can share specific findings.

## Tasks

| # | Task | Priority | Est. | Done |
| --- | --- | --- | --- | --- |
| 1 | Add URL parameter parsing on page load (?park=CODE) | High | 20 min | ☐ |
| 2 | Auto-open popup and zoom to park when deep link detected | High | 30 min | ☐ |
| 3 | Update URL hash when user clicks a park marker | Medium | 20 min | ☐ |
| 4 | Add “Copy Link” button to park popup panel | Medium | 30 min | ☐ |
| 5 | Test across browsers and in embed mode | High | 20 min | ☐ |
| 6 | Commit and push | Medium | 10 min | ☐ |

## Deliverable

Shareable URLs that open directly to a specific park’s popup

## Risk / Notes

Embed mode (iframe) may block URL parameter access — need postMessage fallback

# Sprint 4: SEO & Social Sharing Meta Tags

| Status: | Planned |
| --- | --- |
| Duration: | 1 session |

## Goal

Add Open Graph and Twitter Card meta tags so the site shows a compelling preview when shared on social media or messaging platforms.

## Tasks

| # | Task | Priority | Est. | Done |
| --- | --- | --- | --- | --- |
| 1 | Create OG image (1200x630) with map preview and title | High | 30 min | ☐ |
| 2 | Add Open Graph meta tags (og:title, og:description, og:image, og:url) | High | 15 min | ☐ |
| 3 | Add Twitter Card meta tags (twitter:card, twitter:title, etc.) | High | 10 min | ☐ |
| 4 | Add structured data (JSON-LD) for search engines | Medium | 20 min | ☐ |
| 5 | Add “Last Updated” date display on the page | Medium | 15 min | ☐ |
| 6 | Test with Facebook Sharing Debugger and Twitter Card Validator | High | 15 min | ☐ |
| 7 | Commit and push | Medium | 10 min | ☐ |

## Deliverable

Rich social media previews when URL is shared; visible last-updated date

## Risk / Notes

GitHub Pages caching may delay OG image updates

# Sprint 5: Mobile Optimization

| Status: | Planned |
| --- | --- |
| Duration: | 1–2 sessions |

## Goal

Ensure the map, controls, popups, and photo galleries render well on mobile devices (phones and tablets).

## Tasks

| # | Task | Priority | Est. | Done |
| --- | --- | --- | --- | --- |
| 1 | Audit current mobile rendering (controls bar, search, filters) | High | 20 min | ☐ |
| 2 | Add responsive breakpoints for controls bar layout | High | 45 min | ☐ |
| 3 | Optimize popup panel width and photo grid for small screens | High | 30 min | ☐ |
| 4 | Ensure touch-friendly tap targets (44px minimum) | Medium | 20 min | ☐ |
| 5 | Test on iOS Safari, Android Chrome, and tablet viewports | High | 30 min | ☐ |
| 6 | Commit and push | Medium | 10 min | ☐ |

## Deliverable

Fully responsive layout across phone, tablet, and desktop

## Risk / Notes

Leaflet.js popups have limited mobile customization out of the box

# Sprint 6: Photo Lightbox

| Status: | Backlog |
| --- | --- |
| Duration: | 1 session |

## Goal

Add a full-screen lightbox overlay when users click before/after/restored photos, with zoom and navigation.

## Tasks

| # | Task | Priority | Est. | Done |
| --- | --- | --- | --- | --- |
| 1 | Implement lightbox overlay component (CSS + JS) | Medium | 45 min | ☐ |
| 2 | Add keyboard navigation (arrow keys, Escape to close) | Medium | 20 min | ☐ |
| 3 | Add pinch-to-zoom support for mobile | Medium | 30 min | ☐ |
| 4 | Wire up all sosPhotoUrls click handlers | Medium | 15 min | ☐ |
| 5 | Test across browsers | Medium | 15 min | ☐ |
| 6 | Commit and push | Low | 10 min | ☐ |

## Deliverable

Click-to-expand photo viewer with navigation and zoom

## Risk / Notes

Adding a lightbox library increases page weight; consider building lightweight custom solution

# Sprint 7: Performance — Split parkData

| Status: | Backlog |
| --- | --- |
| Duration: | 1–2 sessions |

## Goal

Extract the ~1.5MB parkData JSON from index.html into a separate file loaded asynchronously, reducing initial page load time.

## Tasks

| # | Task | Priority | Est. | Done |
| --- | --- | --- | --- | --- |
| 1 | Extract parkData JSON to separate parks.json file | Medium | 20 min | ☐ |
| 2 | Add async fetch + loading spinner on page load | Medium | 30 min | ☐ |
| 3 | Add error handling for failed data fetch | Medium | 15 min | ☐ |
| 4 | Enable gzip/brotli compression via GitHub Pages headers | Low | 15 min | ☐ |
| 5 | Benchmark before/after load times | Medium | 20 min | ☐ |
| 6 | Commit and push | Low | 10 min | ☐ |

## Deliverable

Page loads with lightweight HTML shell, then fetches park data async

## Risk / Notes

GitHub Pages may not support custom compression headers; need to test cache behavior