## Sprint Overview
MissingParkHistory.org — IT Project Plan
Full Roadmap Refresh ¦ Version 2.0 ¦ March 24, 2026 ¦ Sprints = ~5 min Claude Cowork/Code dev cycles
Sprint | Name | Status | Tasks | Completed | % Done | Priority | Notes
Sprint 1 | Narrative Audit & Data Fixes | Done | 8 | 8 | 100% | P0 — Critical | Fix wrong park names, narratives, states. Commit eb8ffb4.
Sprint 2 | Wayback Link Verification | Done | 5 | 5 | 100% | P1 — High | Verify SOS Tracker links, add Wayback Machine URLs.
Sprint 3 | Deep Linking & Shareable URLs | Done | 6 | 6 | 100% | P0 — Critical | URL-addressable entries (e.g., /glacier/climate). Commit b24dc1c.
Sprint 4 | SEO & Social Meta Tags | Done | 8 | 8 | 100% | P0 — Critical | OG tags, Twitter cards, JSON-LD, favicon, og-image.png. Commit 8adb48d.
Sprint 5 | Mobile Optimization | Done | 7 | 7 | 100% | P0 — Critical | Responsive layout, touch targets, carousel fix. Commit d0fc6bb.
Sprint 6 | Photo Lightbox & Multi-Select Filters | Done | 9 | 9 | 100% | P1 — High | Lightbox gallery, multi-select dropdowns, async data. Commit af78ba7.
Sprint 7 | Take Action Feature | Done | 10 | 10 | 100% | P1 — High | Contact reps, clipboard copy, Resistbot, ZIP tracker. Commits c2dfa65–9c747df.
Sprint 8 | SEO Phase 2 — Content Pages | To Do | 6 | 0 | 0% | P0 — Critical | Create /about and /data-methodology pages per SEO plan. High E-E-A-T value.
Sprint 9 | SEO Phase 3 — Keyword & Link Building | To Do | 5 | 0 | 0% | P1 — High | Target keyword table, blog/explainer posts, pitch press outreach.
Sprint 10 | Performance & Data Split | To Do | 6 | 0 | 0% | P1 — High | Split parkData into lazy-loaded JSON, lighthouse audit, caching headers.
Sprint 11 | Analytics & Search Console | To Do | 4 | 0 | 0% | P2 — Medium | Google Search Console, sitemap.xml, analytics integration.
Sprint 12 | SSR Social Cards & Advanced SEO | To Do | 5 | 0 | 0% | P2 — Medium | Per-park OG cards via Cloudflare Workers, dynamic meta for deep links.
TOTALS |  |  | 79 | 53 | 67.09%

## Task Backlog
Detailed Task Backlog — All Sprints
Sprint | Task ID | Task | Status | Priority | Est. (min) | Owner | Git Commit | Notes
Sprint 1 | 1.1 | Fix Rock Creek Park narrative (was Rocky Mtn NP) | Done | P0 | 1 | Claude | 05b0f7a
Sprint 1 | 1.2 | Fix 6 park entries with wrong names/narratives | Done | P0 | 2 | Claude | eb8ffb4
Sprint 1 | 1.3 | Label FWS photos as Sierra Club exhibit docs | Done | P1 | 1 | Claude | f516294
Sprint 1 | 1.4 | Wire FWS-001/FWS-009 exhibit photos | Done | P1 | 1 | Claude | f1ef964
Sprint 1 | 1.5 | Add after + restored photos from SOS Tracker | Done | P1 | 1 | Claude | 9fce924
Sprint 1 | 1.6 | Fix Entry #386 Belmont-Paul NM | Done | P0 | 1 | Claude | 2596e3a
Sprint 1 | 1.7 | Fix Theodore Roosevelt NP location MT→ND | Done | P0 | 1 | Claude | 58692d5
Sprint 1 | 1.8 | Fix Unknown Park placeholders in 4 entries | Done | P0 | 1 | Claude | b40603a
Sprint 2 | 2.1 | Audit SOS Tracker Wayback links | Done | P1 | 1 | Claude
Sprint 2 | 2.2 | Add missing Wayback Machine URLs | Done | P1 | 1 | Claude
Sprint 2 | 2.3 | Verify before/after photo URLs resolve | Done | P1 | 1 | Claude
Sprint 2 | 2.4 | Clean broken image references | Done | P2 | 1 | Claude
Sprint 2 | 2.5 | QA all links in parkData | Done | P1 | 1 | Claude
Sprint 3 | 3.1 | Build deep link URL scheme (?park=X) | Done | P0 | 1 | Claude | b24dc1c
Sprint 3 | 3.2 | Parse URL params on page load | Done | P0 | 1 | Claude | b24dc1c
Sprint 3 | 3.3 | Auto-open panel for deep-linked entry | Done | P0 | 1 | Claude | b24dc1c
Sprint 3 | 3.4 | Update URL on panel open (pushState) | Done | P1 | 1 | Claude | b24dc1c
Sprint 3 | 3.5 | Add Share button with copy-to-clipboard | Done | P1 | 1 | Claude | b24dc1c
Sprint 3 | 3.6 | Test deep links across browsers | Done | P1 | 1 | Claude
Sprint 4 | 4.1 | Add <title> tag with primary keyword | Done | P0 | 1 | Claude | 8adb48d | SEO Plan §1
Sprint 4 | 4.2 | Add meta description (155 chars) | Done | P0 | 1 | Claude | 8adb48d | SEO Plan §1
Sprint 4 | 4.3 | Add Open Graph tags (title, desc, image, url) | Done | P0 | 1 | Claude | 8adb48d | SEO Plan §2
Sprint 4 | 4.4 | Add Twitter Card tags (summary_large_image) | Done | P0 | 1 | Claude | 8adb48d | SEO Plan §3
Sprint 4 | 4.5 | Add canonical URL + robots directive | Done | P1 | 1 | Claude | 8adb48d | SEO Plan §1
Sprint 4 | 4.6 | Add inline SVG favicon | Done | P2 | 1 | Claude | 8adb48d | SEO Plan §4
Sprint 4 | 4.7 | Add JSON-LD structured data (WebApplication) | Done | P1 | 1 | Claude | 8adb48d | SEO Plan §5
Sprint 4 | 4.8 | Create og-image.png (1200×630 social card) | Done | P0 | 2 | Claude | 8adb48d | SEO Plan §6
Sprint 5 | 5.1 | Responsive CSS for mobile viewports | Done | P0 | 1 | Claude | d0fc6bb
Sprint 5 | 5.2 | Touch-friendly tap targets (44px min) | Done | P0 | 1 | Claude | d0fc6bb
Sprint 5 | 5.3 | Fix carousel arrow navigation bug | Done | P0 | 1 | Claude | d0fc6bb
Sprint 5 | 5.4 | Stack filters at top on mobile | Done | P1 | 1 | Claude | 7c6644e
Sprint 5 | 5.5 | Legend at bottom on mobile | Done | P1 | 1 | Claude | 7c6644e
Sprint 5 | 5.6 | Fix dropdown option contrast | Done | P2 | 1 | Claude | f2cd85c
Sprint 5 | 5.7 | Compact embed mode layout | Done | P1 | 1 | Claude | 5dcdde2
Sprint 6 | 6.1 | Photo lightbox with prev/next navigation | Done | P0 | 2 | Claude | af78ba7
Sprint 6 | 6.2 | Multi-select filter dropdowns | Done | P0 | 2 | Claude | af78ba7
Sprint 6 | 6.3 | Async data loading for parkData | Done | P1 | 1 | Claude | af78ba7
Sprint 6 | 6.4 | Add 'Has Photos' media filter | Done | P1 | 1 | Claude | 7ee065c
Sprint 6 | 6.5 | Fix Entry #904 (Voyageurs NP) | Done | P0 | 1 | Claude | 7ee065c
Sprint 6 | 6.6 | Normalize FWS topic names | Done | P1 | 1 | Claude | 432cd00
Sprint 6 | 6.7 | Fix filter chip z-index/overlap issues | Done | P1 | 1 | Claude | b440e56
Sprint 6 | 6.8 | Fix NTR filter from spreadsheet | Done | P0 | 1 | Claude | 0878127
Sprint 6 | 6.9 | Fix critical scope/safety issues | Done | P0 | 1 | Claude | 7851445
Sprint 7 | 7.1 | Build Take Action button UI | Done | P0 | 1 | Claude | c2dfa65
Sprint 7 | 7.2 | Clipboard copy for rep contact info | Done | P0 | 1 | Claude | 59fed60
Sprint 7 | 7.3 | Contact form links for reps | Done | P0 | 1 | Claude | 59fed60
Sprint 7 | 7.4 | Resistbot integration | Done | P1 | 1 | Claude | c2dfa65
Sprint 7 | 7.5 | Rebuild reps from House Clerk data | Done | P0 | 2 | Claude | 72860ff
Sprint 7 | 7.6 | Build zipToDistrict from Census crosswalk | Done | P0 | 2 | Claude | c2dfa65
Sprint 7 | 7.7 | ZIP code tracker (hidden admin panel) | Done | P2 | 1 | Claude | 3cda10f
Sprint 7 | 7.8 | Fix 20 stale reps | Done | P0 | 1 | Claude | c2dfa65
Sprint 7 | 7.9 | Reposition buttons below zoom controls | Done | P1 | 1 | Claude | 1f32a73
Sprint 7 | 7.10 | Add Huffman signer detection | Done | P1 | 1 | Claude | 9c747df
Sprint 8 | 8.1 | Create /about page (project story, sourcing) | To Do | P0 | 2 | Claude |  | SEO Plan §2 — Builds E-E-A-T
Sprint 8 | 8.2 | Create /data-methodology page | To Do | P0 | 2 | Claude |  | SEO Plan §2 — Explain leaked DB, Wayback
Sprint 8 | 8.3 | Link coverage articles on /about | To Do | P1 | 1 | Claude |  | Outside Mag, Condé Nast Traveler backlinks
Sprint 8 | 8.4 | Add dynamic document.title in openPanel() | To Do | P1 | 1 | Claude |  | SEO Plan — improves tab/bookmarks
Sprint 8 | 8.5 | Reset document.title in closePanel() | To Do | P2 | 1 | Claude
Sprint 8 | 8.6 | QA all new pages for mobile + accessibility | To Do | P1 | 1 | Claude
Sprint 9 | 9.1 | Write 'NPS censorship' explainer/blog post | To Do | P0 | 3 | Claude |  | SEO Plan keyword table — Medium volume
Sprint 9 | 9.2 | Write 'SO 3431' policy framework page | To Do | P1 | 2 | Claude |  | Niche but high-intent keyword
Sprint 9 | 9.3 | Create individual park pages for top entries | To Do | P0 | 3 | Claude |  | Biggest SEO opportunity per plan
Sprint 9 | 9.4 | Pitch to press: Outside, Guardian, Grist, local papers | To Do | P1 | 2 | Mike | N/A | SEO Plan §4 — link building
Sprint 9 | 9.5 | Post to Reddit r/NationalPark, r/camping | To Do | P2 | 1 | Mike | N/A | SEO Plan §4 — viral + backlinks
Sprint 10 | 10.1 | Split parkData into lazy-loaded JSON chunks | To Do | P0 | 3 | Claude |  | Currently all inline in index.html
Sprint 10 | 10.2 | Run Lighthouse audit and fix top issues | To Do | P0 | 2 | Claude
Sprint 10 | 10.3 | Add caching headers / service worker | To Do | P1 | 2 | Claude
Sprint 10 | 10.4 | Optimize image loading (lazy load, WebP) | To Do | P1 | 2 | Claude
Sprint 10 | 10.5 | Minify CSS/JS in index.html | To Do | P2 | 1 | Claude
Sprint 10 | 10.6 | Verify sub-3s load on mobile 3G | To Do | P1 | 1 | Claude
Sprint 11 | 11.1 | Submit sitemap.xml to Google Search Console | To Do | P0 | 1 | Mike | N/A | SEO Plan §3
Sprint 11 | 11.2 | Generate sitemap.xml from parkData | To Do | P0 | 2 | Claude
Sprint 11 | 11.3 | Add privacy-respecting analytics (Plausible/Umami) | To Do | P1 | 2 | Claude
Sprint 11 | 11.4 | Monitor Search Console for crawl errors | To Do | P2 | 1 | Mike | N/A | Ongoing
Sprint 12 | 12.1 | Set up Cloudflare Worker for SSR meta tags | To Do | P1 | 3 | Claude |  | Per-park social cards
Sprint 12 | 12.2 | Generate per-park OG images dynamically | To Do | P1 | 3 | Claude
Sprint 12 | 12.3 | Test with Facebook/Twitter/LinkedIn validators | To Do | P1 | 1 | Claude |  | SEO Plan checklist §4
Sprint 12 | 12.4 | Clear social platform caches | To Do | P2 | 1 | Claude |  | Facebook debugger re-scrape
Sprint 12 | 12.5 | Implement Dataset schema.org markup | To Do | P2 | 1 | Claude |  | SEO Plan §5 — Dataset schema

## SEO Keywords
SEO Keyword Targets — from SEO Strategy & Action Plan v1.0
Target Keyword | Search Volume | Your Play | Sprint
"national park signs removed" | High & rising | Homepage already targets this — you own #1 | Sprint 4 (Done)
"NPS censorship" | Medium | Blog post or explainer page | Sprint 9
[individual park name] + history | Low per park; huge in aggregate | Individual park pages — biggest SEO opportunity | Sprint 9
"save national parks" | Medium | Explainer showing how site complements SOS campaigns | Sprint 9
"SO 3431" / "secretarial order 3431" | Niche but high-intent | Content on the legal/policy framework | Sprint 9

## Risks & Dependencies
Risk Register & Dependencies
Risk / Dependency | Impact | Likelihood | Mitigation | Affects Sprint
Social crawlers don't execute JS — deep link meta tags show generic info | Medium | Certain | Sprint 12 adds SSR via Cloudflare Workers | Sprint 12
Press outreach requires manual follow-up (not automatable) | High | Medium | Mike owns outreach; Claude drafts pitch templates | Sprint 9
Google Search Console requires domain verification | Medium | Low | Mike verifies via DNS TXT record | Sprint 11
parkData inline in index.html causes slow initial load | High | Certain | Sprint 10 splits into lazy-loaded JSON | Sprint 10
Facebook OG cache may show stale previews after tag updates | Low | High | Use Facebook Debugger to re-scrape after deploy | Sprint 12
Individual park pages could be thousands of routes | Medium | Medium | Start with top 20 entries by photo count; expand iteratively | Sprint 9
Rep data goes stale as Congress changes | Medium | Certain | Rebuild from House Clerk data periodically | Sprint 7 (ongoing)