## Roadmap
MissingParkHistory.org — IT Project Plan
Sprint Roadmap ¦ Owner: Mike Beebe (BULLMOOSE1872) ¦ Date: March 20, 2026
# | Sprint | Status | Duration | Priority | Goal | Deliverable | Risk / Notes
1 | Sprint 1: Data Quality — Narrative Audit | Up Next | 1–2 sessions | Critical | Scan all 874 park entries for mismatched narratives. Fix all incorrect text and verify geographic accuracy. | Zero narrative/park mismatches across all 874 entries | Some narratives may be intentionally generic — need to distinguish boilerplate from errors
2 | Sprint 2: Data Quality — Wayback Link Verification | Planned | 1 session | High | Verify all Wayback Machine archive links resolve correctly. Fix or remove broken links. | All wayback links verified working or flagged for manual review | Wayback Machine rate limits may slow bulk checking
3 | Sprint 3: Deep Linking / Shareable Park URLs | Planned | 1 session | High | Enable direct links to individual park entries so users and journalists can share specific findings. | Shareable URLs that open directly to a specific park's popup | Embed mode (iframe) may block URL parameter access — need postMessage fallback
4 | Sprint 4: SEO & Social Sharing Meta Tags | Planned | 1 session | High | Add Open Graph and Twitter Card meta tags for compelling social media previews. | Rich social media previews when URL is shared; visible last-updated date | GitHub Pages caching may delay OG image updates
5 | Sprint 5: Mobile Optimization | Planned | 1–2 sessions | Medium | Ensure the map, controls, popups, and photo galleries render well on mobile devices. | Fully responsive layout across phone, tablet, and desktop | Leaflet.js popups have limited mobile customization out of the box
6 | Sprint 6: Photo Lightbox | Backlog | 1 session | Medium | Add full-screen lightbox overlay for before/after/restored photos with zoom and navigation. | Click-to-expand photo viewer with navigation and zoom | Adding a lightbox library increases page weight; consider lightweight custom solution
7 | Sprint 7: Performance — Split parkData | Backlog | 1–2 sessions | Medium | Extract parkData JSON into a separate file loaded asynchronously to reduce initial page load. | Page loads with lightweight HTML shell, then fetches park data async | GitHub Pages may not support custom compression headers; need to test cache behavior

## Sprint 1
Sprint 1: Data Quality — Narrative Audit
Status: | Up Next
Duration: | 1–2 sessions
Priority: | Critical
Goal
Scan all 874 park entries for mismatched narratives. Fix all incorrect text and verify geographic accuracy.
Tasks
# | Task | Priority | Est. | Done
1 | Write script to compare park code/name against narrative text | Critical | 30 min | ☐
2 | Flag entries where narrative mentions a different park name | Critical | 15 min | ☐
3 | Flag entries where context-box references wrong park stats | Critical | 15 min | ☐
4 | Manually review and correct each flagged entry | Critical | 1–2 hrs | ☐
5 | Cross-check GPS coordinates against park code locations | High | 30 min | ☐
6 | Commit and push all corrections | High | 10 min | ☐
7 | Verify corrections on live site | High | 15 min | ☐
Deliverable
Zero narrative/park mismatches across all 874 entries
Risk / Notes
Some narratives may be intentionally generic — need to distinguish boilerplate from errors

## Sprint 2
Sprint 2: Data Quality — Wayback Link Verification
Status: | Planned
Duration: | 1 session
Priority: | High
Goal
Verify all Wayback Machine archive links resolve correctly. Fix or remove broken links.
Tasks
# | Task | Priority | Est. | Done
1 | Extract all wayback URLs from parkData | High | 15 min | ☐
2 | Batch-check URL response status codes | High | 30 min | ☐
3 | Report broken/redirected links | High | 15 min | ☐
4 | Update or remove broken wayback references | Medium | 30 min | ☐
5 | Commit and verify on live site | Medium | 10 min | ☐
Deliverable
All wayback links verified working or flagged for manual review
Risk / Notes
Wayback Machine rate limits may slow bulk checking

## Sprint 3
Sprint 3: Deep Linking / Shareable Park URLs
Status: | Planned
Duration: | 1 session
Priority: | High
Goal
Enable direct links to individual park entries so users and journalists can share specific findings.
Tasks
# | Task | Priority | Est. | Done
1 | Add URL parameter parsing on page load (?park=CODE) | High | 20 min | ☐
2 | Auto-open popup and zoom to park when deep link detected | High | 30 min | ☐
3 | Update URL hash when user clicks a park marker | Medium | 20 min | ☐
4 | Add 'Copy Link' button to park popup panel | Medium | 30 min | ☐
5 | Test across browsers and in embed mode | High | 20 min | ☐
6 | Commit and push | Medium | 10 min | ☐
Deliverable
Shareable URLs that open directly to a specific park's popup
Risk / Notes
Embed mode (iframe) may block URL parameter access — need postMessage fallback

## Sprint 4
Sprint 4: SEO & Social Sharing Meta Tags
Status: | Planned
Duration: | 1 session
Priority: | High
Goal
Add Open Graph and Twitter Card meta tags for compelling social media previews.
Tasks
# | Task | Priority | Est. | Done
1 | Create OG image (1200x630) with map preview and title | High | 30 min | ☐
2 | Add Open Graph meta tags | High | 15 min | ☐
3 | Add Twitter Card meta tags | High | 10 min | ☐
4 | Add structured data (JSON-LD) for search engines | Medium | 20 min | ☐
5 | Add 'Last Updated' date display on the page | Medium | 15 min | ☐
6 | Test with Facebook Sharing Debugger and Twitter Card Validator | High | 15 min | ☐
7 | Commit and push | Medium | 10 min | ☐
Deliverable
Rich social media previews when URL is shared; visible last-updated date
Risk / Notes
GitHub Pages caching may delay OG image updates

## Sprint 5
Sprint 5: Mobile Optimization
Status: | Planned
Duration: | 1–2 sessions
Priority: | Medium
Goal
Ensure the map, controls, popups, and photo galleries render well on mobile devices.
Tasks
# | Task | Priority | Est. | Done
1 | Audit current mobile rendering | High | 20 min | ☐
2 | Add responsive breakpoints for controls bar layout | High | 45 min | ☐
3 | Optimize popup panel width and photo grid for small screens | High | 30 min | ☐
4 | Ensure touch-friendly tap targets (44px minimum) | Medium | 20 min | ☐
5 | Test on iOS Safari, Android Chrome, and tablet viewports | High | 30 min | ☐
6 | Commit and push | Medium | 10 min | ☐
Deliverable
Fully responsive layout across phone, tablet, and desktop
Risk / Notes
Leaflet.js popups have limited mobile customization out of the box

## Sprint 6
Sprint 6: Photo Lightbox
Status: | Backlog
Duration: | 1 session
Priority: | Medium
Goal
Add full-screen lightbox overlay for before/after/restored photos with zoom and navigation.
Tasks
# | Task | Priority | Est. | Done
1 | Implement lightbox overlay component (CSS + JS) | Medium | 45 min | ☐
2 | Add keyboard navigation (arrow keys, Escape) | Medium | 20 min | ☐
3 | Add pinch-to-zoom support for mobile | Medium | 30 min | ☐
4 | Wire up all sosPhotoUrls click handlers | Medium | 15 min | ☐
5 | Test across browsers | Medium | 15 min | ☐
6 | Commit and push | Low | 10 min | ☐
Deliverable
Click-to-expand photo viewer with navigation and zoom
Risk / Notes
Adding a lightbox library increases page weight; consider lightweight custom solution

## Sprint 7
Sprint 7: Performance — Split parkData
Status: | Backlog
Duration: | 1–2 sessions
Priority: | Medium
Goal
Extract parkData JSON into a separate file loaded asynchronously to reduce initial page load.
Tasks
# | Task | Priority | Est. | Done
1 | Extract parkData JSON to separate parks.json file | Medium | 20 min | ☐
2 | Add async fetch + loading spinner on page load | Medium | 30 min | ☐
3 | Add error handling for failed data fetch | Medium | 15 min | ☐
4 | Enable gzip/brotli compression via GitHub Pages headers | Low | 15 min | ☐
5 | Benchmark before/after load times | Medium | 20 min | ☐
6 | Commit and push | Low | 10 min | ☐
Deliverable
Page loads with lightweight HTML shell, then fetches park data async
Risk / Notes
GitHub Pages may not support custom compression headers; need to test cache behavior